## Prerequisites
# | Prerequisite | Details | Owner | Status
1 | Relearn Task Unit registered in master deliver app | Staging HQ app '[08/12] Delivey App' (domain connectqa-automation): form 'relearn_module' registered as Task Unit, slug 'relearn_task', name 'Relearn Task Unit'. Verified via CCZ download 30-Jul-2026. Recommended: also 'Make New Version' (Released) on the master so manual testing/mobile sync sees it. Automation copies take the saved state, so per-run opportunities already inherit it. | Nitin (done) | Done - build pending
2 | Waffle switch 'worker_visits_tasks' active on staging | Gates the Visits/Tasks tabs on the worker drill-down and the dashboard 'Tasks Assigned to Connect Workers' tile. Task pages themselves are NOT gated. Check Django admin > Waffle > Switches on connect-staging. | Nitin / admin | To confirm
3 | Designated static opportunity with enrolled worker(s) | Needed for assignment/list/deletion flows: a managed opportunity whose program org is one where the QA user is an org ADMIN (PM org, e.g. PM_Automation_01), with >=1 worker with accepted invite, not suspended. Its deliver app must ALSO get the relearn task unit registered + new released version (task types are per opportunity deliver app). Record org slug + opp id in test data. | Nitin | To designate
4 | QA credentials & roles | Existing single CCHQ account in settings.cfg / CI secrets (env vars hq_username/hq_password); Connect access via 'Login with CommCareHQ' OAuth. Role switching via Connect org switcher: PM org (admin) for manage flows, NM org for permission-negative tests. A viewer-role account does not exist yet (viewer test cases marked manual). | Existing | Ready
5 | Framework additions (code) | New page objects: connect_task_types_page, connect_assigned_tasks_page, workers Tasks tab; new sections in playwright_web/locators/web_locators.yaml; new keys in test_data/web_test_data.yaml (slug 'relearn_task', static opp reference); refactor test_olp_01_02_03 setup into reusable helpers/fixtures. Cleanup: stale learn_app/deliver_app yaml keys ('Learn App [Job 1]'/'Delivey App [Job 2]') no longer match reality. | Claude | Phase 1 scope
6 | Phase 2 (hybrid) prerequisites | BrowserStack Maestro setup (exists from mobile suite); staging-pointed mobile app build; dedicated worker test account; NEW Maestro flows: worker login, accept opportunity invite, sync, open & submit relearn form, assert in-app pending-task warning; orchestration glue (pytest triggers BrowserStack run between web phases, polls result). Not started. | Claude + Nitin | Phase 2 scope
7 | Known gaps / out of scope | OCS-mode (chatbot) tasks: no web UI to configure mode/chatbot (Django admin only), needs connected Open Chat Studio account - reviewed and skipped (note related open bug CCCT-2699). Push notifications: not web-verifiable, covered only as Phase 2 mobile checks. Task completion cannot be driven from web (form receiver / mobile only). Task-unit lookups cached 1h on Connect side (affects newly built apps on existing opportunities). | - | Noted
8 | Automation shape agreed 30-Jul-2026 | Plan cases collapse into 4 Phase 1 journey tests (J1 config, J2 assignment lifecycle, J3 views/filters, J4 permissions) + 2 Phase 2 hybrid tests (P2-A relearn lifecycle incl. warning-cleared check, P2-B visit blocking). Cases marked 'Deferred' or 'Manual only' are intentionally not automated - see Automation Target column on each tab. | Agreed | Ready

## Task Type Configuration
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Happy path (runs against a FRESH opportunity created by the reusable OLP setup flow - new app copy each run, so the slug is always available)
TC-TTC-001 | Open Configure Task Types page | 1. Complete reusable setup (login, program, opportunity) 2. From opportunity dashboard open the three-dot menu 3. Click 'Configure Task Types' | Page loads at /{org}/opportunity/{id}/task_types/; shows 'Connected Delivery App: <copied app name>'; empty task type table; 'Add New Task Type' button visible | 1 - Web (Playwright) | J1 test_task_type_config |  | Menu entry only rendered for PM (request.is_opportunity_pm)
TC-TTC-002 | Create a task type from the registered task unit | 1. Click 'Add New Task Type' 2. In the modal select Task Unit 'Relearn Task Unit' 3. Verify Name/Description auto-fill 4. Enter case property (e.g. relearn_complete) 5. Save | Modal closes; table shows new row: name 'Relearn Task Unit', Linked Task Unit 'relearn_task', not archived | 1 - Web (Playwright) | J1 test_task_type_config |  | Modal is Alpine x-if (absent from DOM until opened); Name/Description auto-fill via onTaskUnitSelectChange
TC-TTC-003 | Slug integrity | 1. After selecting the task unit in the Add modal, read the selected option's value - it becomes the TaskType slug | Selected option value equals 'relearn_task' exactly. NOTE: the slug is never rendered on the page; the Linked Task Unit column shows the unit display name (verified on staging 30-Jul-2026) | 1 - Web (Playwright) | J1 test_task_type_config |  | Slug mismatch breaks completion matching (case-sensitive)
TC-TTC-004 | Used task unit removed from dropdown | 1. Click 'Add New Task Type' again after TC-TTC-002 | Task Unit dropdown no longer offers 'Relearn Task Unit'; if it was the only unit, shows 'No available task units' with disabled control | 1 - Web (Playwright) | J1 test_task_type_config |  | Unique (app, slug) constraint; already-used slugs filtered out
TC-TTC-005 | Edit task type name/description | 1. Click Edit on the task type row 2. Change name and description 3. Save | HX-Redirect back to config page; row shows updated values | 1 - Web (Playwright) | J1 test_task_type_config
TC-TTC-006 | Archive task type | 1. Edit the task type 2. Tick 'Archive this task type' 3. Save | Row STAYS in the config table with the archive date (MM/DD/YYYY) in the Archived column (confirmed by Nitin + network-instrumented staging run 30-Jul-2026); type excluded from Create Task dropdown | 1 - Web (Playwright) | J1 test_task_type_config |  | Archive sets archived=now, is_active=False. Config table also has a Mode column (relearn/ocs). Also covers TAS-005 on the fresh opp
Edge cases
TC-TTC-007 | Task unit fetch failure handling | 1. Open Add Task Type modal when HQ CCZ download fails (e.g. app has no build) | Dropdown shows 'Failed to load task units' and is disabled; no crash | Manual / one-off | Manual only |  | Hard to trigger deterministically on staging - verify once manually

## Task Assignment
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Happy path (runs against the DESIGNATED STATIC opportunity with enrolled worker; task type pre-created once)
TC-TAS-001 | Assign a task to a worker | 1. Open /{org}/opportunity/{id}/assigned_tasks/ 2. Click the Create Task icon button (tooltip 'Create Task') 3. Select Task type and Connect Worker (TomSelect dropdowns) 4. Set due date = today+7 5. Save Changes | Message 'Task created successfully.'; new row: worker name+username, status badge 'To Do' (amber), task type name, Assigned Date = today, correct Due Date, Assigned By = QA user | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | Create button is icon-only; form posts via HTMX, success = HX-Redirect + Django message
TC-TAS-002 | Duplicate assignment blocked | 1. With TC-TAS-001 task still pending, repeat the same assignment (same type + worker) | Validation error in modal: 'This task type is already assigned to the selected worker.'; no new row | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | DB constraint unique (task_type, opportunity_access) while status=assigned
TC-TAS-003 | Past due date rejected | 1. Open Create Task modal 2. Attempt due date in the past (force via JS - input min=today) 3. Submit | Server-side validation error; task not created | 1 - Web (Playwright) | Deferred |  | Bypassing the UI to test server validation is weak signal in UI automation - candidate for a future API-level check
TC-TAS-004 | Worker dropdown eligibility | 1. Open Create Task modal 2. Inspect Connect Worker options | Only workers with accepted invite and not suspended are listed | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | J2 asserts the positive case (eligible worker listed). Exclusion assertions need specially staged worker states - manual
TC-TAS-005 | Task dropdown excludes inactive/archived types | 1. Archive a task type 2. Open Create Task modal | Archived/inactive task types not offered | 1 - Web (Playwright) | J1 test_task_type_config |  | Verified on the fresh opportunity within J1 (avoids mutating shared static data)
TC-TAS-006 | Edit assigned task due date | 1. On the task row click Edit 2. Set 'New End Date' = today+14, enter a reason 3. Save | Message 'Task updated successfully.'; row shows new due date | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | Edit button rendered only for status=assigned rows; due_date changes tracked via pghistory
TC-TAS-007 | Metric cards update | 1. Record Total/Open/Complete card values 2. Assign a task 3. Re-check | Total and Open increment by 1; Complete unchanged | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle
Edge cases
TC-TAS-008 | Assign from worker detail page | 1. Open a worker's Tasks tab (user_tasks page) 2. Create task from there | Worker field is preset (hidden input); task created for that worker; types already assigned to them excluded from dropdown | 1 - Web (Playwright) | Deferred |  | Secondary entry point - add later if regressions appear here
TC-TAS-009 | Edit absent on completed tasks | 1. Locate a completed task row | No Edit button on completed rows | 2 - Hybrid (Web+Mobile) | Phase 2 - deferred |  | Needs completed-task data (Phase 2 or seeded)

## Task List & Views
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Happy path
TC-TLV-001 | Task List page structure | 1. Open the Task List page | Heading 'Task List'; metric cards Total Tasks / Open Tasks / Complete consistent with table contents; columns: checkbox, Connect Worker, Status, Task Type, Assigned Date, Due Date, Assigned By, Edit. NO 'Task ID' column | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | Task ID column removed in PR #1375 - assert absence as regression check
TC-TLV-002 | Filters | 1. Open filter modal 2. Filter by status 'To Do'; reset 3. Filter by task type; reset | Table (HTMX target #task-list-table) updates per filter; counts match expectations; reset restores full list | 1 - Web (Playwright) | J3 test_task_views_filters |  | Two representative filters automated (all five share one filterset code path); remaining filters manual/exploratory
TC-TLV-003 | Workers page Tasks tab | 1. Open Opportunity > Workers 2. Click the 'Tasks' tab | Grouped-by-worker accordion table; the assigned worker's group shows the pending task with amber 'To Do' badge | 1 - Web (Playwright) | J3 test_task_views_filters |  | Tab bar: Connect Workers ¦ Learn ¦ Deliver ¦ Payments ¦ Tasks
TC-TLV-004 | Worker drill-down Visits/Tasks tabs | 1. Open a worker from the workers list 2. Switch to the Tasks tab | Per-worker task list loads (HTMX deferred); worker KPI header shows Pending Tasks count matching data | 1 - Web (Playwright) | J3 test_task_views_filters |  | Tabs gated by waffle switch worker_visits_tasks
TC-TLV-005 | Task details panel | 1. On the worker Tasks page click a task row | Right-hand details panel loads: status, assigned by, due date; completed tasks additionally show Completed At/Duration/'View Form in CommCareHQ' link | 1 - Web (Playwright) | J3 test_task_views_filters |  | SUSPECTED PRODUCT BUG: panel template references completed_task.task.* (field is task_type) so Task Name/Description may render blank - verify manually and file bug BEFORE asserting (see TC-IMP-002)
TC-TLV-006 | Dashboard tile | 1. Open opportunity dashboard with >=1 active task type and waffle switch on | 'Tasks Assigned to Connect Workers' tile visible with correct active-task count; clicking it lands on the Task List page | 1 - Web (Playwright) | J3 test_task_views_filters |  | Tile hidden when switch off OR no active task types (see TC-IMP-003)

## Task Deletion
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Happy path
TC-TDL-001 | Delete a single pending task | 1. On Task List select the task's checkbox 2. Click the Delete icon button (tooltip 'Delete Task(s)') 3. Confirm in the 'Delete Tasks' modal | Task removed from list; Open/Total counts decrement; same type + worker becomes assignable again (constraint released) | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | Delete flow doubles as cleanup so assignment tests are repeatable
TC-TDL-002 | Bulk delete | 1. Assign two tasks (different types or workers) 2. Select both checkboxes 3. Delete and confirm | Confirm modal says 2 task(s); both rows removed | 1 - Web (Playwright) | J2 test_task_assignment_lifecycle |  | POST task_ids[] to assigned_tasks/delete/
Edge cases
TC-TDL-003 | Completed tasks not deletable | 1. Select a completed task (with or without pending ones) 2. Delete | Completed tasks silently excluded - remain in list; pending ones in the selection are removed | 2 - Hybrid (Web+Mobile) | Phase 2 - deferred |  | Needs completed-task data
TC-TDL-004 | Case property reset on delete | 1. Delete a pending task whose type sets a case property 2. Check worker usercase in HQ | Case property reset to '' when no other assigned task uses it | Manual / one-off | Manual only |  | Not web-verifiable; would need HQ API check - one-off manual verification

## Permissions
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Role matrix (PR #1381: manage = PM-org admin; edit = any org member; view = any org role incl. viewer)
TC-PRM-001 | PM org admin - full manage | 1. Browse task list via PM org slug as org admin | Create + Delete buttons visible; checkbox column present; Edit buttons present | 1 - Web (Playwright) | J4 test_task_permissions
TC-PRM-002 | NM org member - edit only | 1. Switch organization to the NM org 2. Open the same opportunity's task list | List visible; NO Create/Delete buttons; NO checkbox column; Edit (due date) still available | 1 - Web (Playwright) | J4 test_task_permissions |  | Same QA user via org switcher
TC-PRM-003 | NM org - task type config blocked | 1. As NM org open /{org}/opportunity/{id}/task_types/ directly | 404 'This page is not available.' | 1 - Web (Playwright) | J4 test_task_permissions |  | OpportunityPMRequiredMixin
TC-PRM-004 | Non-PM create/delete endpoints blocked | 1. As NM org POST to assigned_tasks/create/ and delete/ | 404 responses; no mutation | Manual / one-off | Manual only |  | API-level check; optional hardening test
TC-PRM-005 | Viewer role - read only | 1. As an org viewer open the task list | List visible; no manage or edit controls | Manual / one-off | Manual only |  | No viewer account exists yet - manual until one is provisioned

## E2E Relearn (Phase 2)
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Full relearn lifecycle (Playwright web -> Maestro mobile on BrowserStack -> Playwright web)
TC-E2E-001 | Relearn task completed end-to-end | 1. WEB: reusable setup; invite worker; create task type (case property set); assign task 2. MOBILE: worker logs in, accepts invite, syncs; relearn form now visible; completes and submits form 3. WEB: poll Task List | Status badge flips 'To Do' -> 'Complete'; details panel shows Completed At + Duration + 'View Form in CommCareHQ' link (xform id recorded) | 2 - Hybrid (Web+Mobile) | P2-A e2e_relearn_lifecycle |  | Form receiver matches form task block id to slug 'relearn_task'; allow sync + processing latency in polling
TC-E2E-002 | Pending task blocks delivery visits (CI-760) | 1. Assign task to enrolled worker 2. MOBILE: submit a delivery visit while task pending 3. WEB: open visit verification | Visit auto-rejected with flag 'Pending Task' / 'Worker has an incomplete assigned task.' | 2 - Hybrid (Web+Mobile) | P2-B e2e_visit_blocking |  | Enforced in form receiver process_deliver_unit
TC-E2E-003 | Completion unblocks delivery | 1. Complete the pending task (mobile) 2. Submit a delivery visit | Visit processed normally (not flagged for pending task) | 2 - Hybrid (Web+Mobile) | P2-A e2e_relearn_lifecycle |  | Folded into the P2-A chain after completion step
TC-E2E-006 | In-app pending-task warning cleared after completion | 1. MOBILE: after task assignment, verify the warning message that the task must be completed before continuing delivery activities is displayed 2. Complete the task and sync 3. Re-check the same screen | Warning displayed while task pending; warning NO LONGER displayed after completion; delivery activities accessible | 2 - Hybrid (Web+Mobile) | P2-A e2e_relearn_lifecycle |  | Directly targets open bug CCCT-2699 ('Warning prompt persists after completing an assigned OCS task') - regression-proven check; fold into P2-A chain
TC-E2E-004 | Archived task type does not block visits | 1. Archive the task type while a task is pending 2. Submit delivery visit | Visit not rejected for pending task | 2 - Hybrid (Web+Mobile) | Phase 2 - deferred |  | Archived/inactive types excluded from blocking check (commit 0675f54f) - diminishing returns once P2-A/P2-B exist
TC-E2E-005 | Push notifications | 1. Assign task; observe device 2. Complete task; observe device | 'New Task Assigned' notification on assign; 'Task Completed' on completion | 2 - Hybrid (Web+Mobile) | Phase 2 - deferred |  | Device-side notification assertion is flaky on cloud devices - manual/exploratory

## Regression & Impact Areas
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Impact Areas (from code review of recent tasking PRs #1359, #1375, #1381, #1384, #1385)
TC-IMP-001 | Assigned By fallback | 1. View a task assigned by a user with blank first/last name | Assigned By shows the user's email (never blank); deleted assignor shows 'Deleted user' | Manual / one-off | Manual only |  | PR #1385; needs a blank-name account - verify once
TC-IMP-002 | Task details Name/Description rendering | 1. Open worker task details panel for any task | Task Name and Description populated (template may reference wrong field - completed_task.task vs task_type) | Manual / one-off | Manual only |  | Suspected latent bug found in code review of user_task_details.html - verify on staging; file bug if blank
TC-IMP-003 | Dashboard tile gating | 1. Fresh opportunity with NO task types yet: check dashboard (tile absent) 2. After creating a task type in J1: re-check (tile present) | Tile 'Tasks Assigned to Connect Workers' hidden when no active task type exists; appears once one does | 1 - Web (Playwright) | J1 test_task_type_config |  | Light version folded into J1 on the fresh opp (avoids archiving all types on shared static data); also hidden when waffle switch off
TC-IMP-004 | Existing OLP regression | 1. Run existing test_olp_01_02_03 + test_olp_04 after framework refactor | Both still pass - setup refactor into reusable helpers must not change behavior | 1 - Web (Playwright) | Existing suite (no new code) |  | Gate for the reuse refactor
TC-IMP-005 | Task-unit cache staleness | 1. Register new task unit + build on an app linked to an EXISTING opportunity 2. Open Add Task Type within the hour | Dropdown may not show the new unit for up to 1h (cache) - document, don't automate | Manual / one-off | Manual only |  | Fresh per-run app copies get a fresh cache key, so Phase 1 unaffected
TC-IMP-006 | OCS-mode tasks | - | Reviewed and skipped: no web UI for mode/chatbot config (Django admin only); requires connected OCS account. Revisit when OCS QA is prioritized | Manual / one-off | Manual only |  | CCCT-2552/PR #1359; open related bug CCCT-2699 covered functionally by TC-E2E-006