## Overview & Prerequisites
# | Prerequisite / Note | Details | Owner | Status
| MODULE | Personal ID - 'Traditional App Install & Login' section (PID_48-PID_62) | Akanksha
| Master plan | CCC_ Mobile App Regression [Master] [v2] > Personal ID Tests tab (Google Sheet, read-only source of truth) | QA
1 | Dedicated unlink worker | One dedicated mobile worker, created + PID-linked via the mobile flow, used ONLY for PID_59 so no other worker/test is affected (Kankana). | Akanksha | To create (mobile phase)
2 | settings.cfg | [creds] hq_username/hq_password + [browserstack] user/key at repo root (gitignored). | Akanksha | Done
3 | Staging HQ domain | connectqa-automation on staging.commcarehq.org; PersonalID Status column confirmed live. | QA | Done
4 | Staging APK | app/app-cccStaging-release.apk for Maestro/BrowserStack mobile runs. | QA | Present
5 | Web env | Python 3.14 venv + playwright + chromium; run: pytest --env=stage tests/test_pid_56_57_58_59.py | Akanksha | Done

## Traditional App Install & Login
Test Case No | Description | Steps to Test | Expected Outcome | Phase | Automation Target | Status | Comments / Notes
Traditional App Install & Login - PID_48 through PID_62 (15 cases; 3 web automated, 5 mobile to do, 1 web built/blocked, 4 deferred-manual)
PID_48 | Verify on logging in on a CC app, user sees a 'Link to Personal ID' pop up | 1. Sign up for personal ID 2. Install CC app using barcode 3. Login to the CC app | - User should see a pop-up to link the MW with the Personal ID, "Do you want to link the login to your PersonalID account? You will not need to type your password in the future." - User should see two options i) Yes ii) No | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_48_link_prompt.yaml | Done | Link-to-PID popup appears after worker password login. VERIFIED on emulator.
PID_49 | Verify on selecting 'No' user is able to log into the CC app | cont from above TC - Select No for the "Do you want to link the login to your PersonalID account? You will not need to type your password in the future." pop up | - On selecting 'NO', user is able to login into the CC app - User is able to submit forms without issue - The pop-up does not appears again when user logs out and login again on the app | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_49_link_declined.yaml | Done | Select No -> logs into app normally. VERIFIED.
PID_50 | Verify user is able to see again the "Link to PID" pop up after 30 days |  | - When user deny the first link pop up, user should see the 2nd prompt after 30 days | Manual / Deferred | Manual | Deferred | 30-day re-prompt is time-dependent (evaluateLinkOffer offer-date logic); cannot reliably automate in a single session.
PID_51 | Confirm the MW is now linked with the PersonalID when user clicks on 'Yes' on the pop-up | - Select Yes for the "Do you want to link the login to your PersonalID account? You will not need to type your password in the future." pop up | - MW should be linked to the PersonalID account - User should not have to enter password again to login | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_51_link_accepted.yaml | Done | Select Yes -> MW linked to PersonalId. VERIFIED.
PID_52 | Verify user can also login on the CC app by entering password | cont to above TC - Login to app using password | - User should be able to login by entering the password | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_53_unlink_prompt.yaml | Done | Password login while linked works (covered by the unlink-prompt journey). VERIFIED.
PID_53 | Verify user is able to see unlink pop up while logging in with password | cont to above TC | - User should also see a Unlink PersonalID pop up "I see you logged in with your password although PersonalID was configured for auto-login. Would you like to sever this login from PersonalID?" - User should see two options i) Yes ii) No | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_53_unlink_prompt.yaml | Done | Unlink-PID popup appears on password login when linked. VERIFIED.
PID_54 | Verify if user selects 'Yes' on the Unlink PersonalID pop-up, MW unlinks | cont to above TC - Login to app using password - Click 'yes' to unlink personal ID | - MW should be unlinked to the Personal ID and user can no longer log into the CC apps using PersonalID - User should only be able to login using password | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_54_unlink_accepted.yaml | Done | Yes on unlink popup -> MW unlinked. VERIFIED.
PID_55 | Confirm on selecting 'No'on the unlink PersonalID option, MW remains linked to the PersonalID | cont to above TC - Login to app using password - Click 'NO' to not unlink personal ID | - User should not be unlinked and should be able to login using the PersonalID | 2 - Mobile (Maestro) | Mobile (Maestro) - maestro_mobile/flows/pid_55_unlink_declined.yaml | Done | No on unlink popup -> stays linked. VERIFIED.
PID_56 | Confirm we see a new column "Personal ID"on mobile workers page on HQ | cont to above TC - Login to app using password - Click 'yes' to unlink personal ID | - User should see a new column "Personal ID Status" on mobile workers page on HQ - User should the following two status for the column i) Not LInked ii) Active | 1 - Web (Playwright) | Web (Playwright) - tests/test_pid_56_57_58_59.py :: test_pid_56_57_58_personalid_unlink_on_mobile_workers | Done | PersonalID Status column present + valid values. PASS on staging.
PID_57 | Confirm when a MW is linked to Personal ID, 'Unlink PersonalID' button is present for Active column | 1. Login CC HQ 2. Naviagte to users >> Mobile workers | - Admin user should see "Unlink PersonalID" button, under Action column with Deactivate button | 1 - Web (Playwright) | Web (Playwright) - tests/test_pid_56_57_58_59.py :: test_pid_56_57_58_personalid_unlink_on_mobile_workers | Done | Unlink PersonalID action present for linked worker. PASS on staging.
PID_58 | Verify on clicking on "Unlink PersonalID" button, user can unlink the MW with PersonalID |  | - On clicking "Unlink PersonalID" option, we see a pop-up on HQ "Are you sure you want to unlink the PersonalID account for this mobile worker?" and see the two options i) Cancel ii) Unlink | 1 - Web (Playwright) | Web (Playwright) - tests/test_pid_56_57_58_59.py :: test_pid_56_57_58_personalid_unlink_on_mobile_workers | Done | Unlink confirm modal (Cancel/Unlink) -> Cancel (non-destructive). PASS on staging.
PID_59 | Confrim on selecting the Unlink option, MW is not linked to the PersonalID anymore |  | - MW should get unlinked from PersonalID and PersonalID status should get updated to Inactive - User should now see a 'Link PersonalID' option for the MW - User should not see the option to login via PersonalID on the CC app | 1 - Web (Playwright), destructive | Web (Playwright) - tests/test_pid_56_57_58_59.py :: test_pid_59_confirm_unlink_flips_status (guarded: RUN_DESTRUCTIVE_PID + PID_UNLINK_WORKER) | Done | Unlink flips status to Not Linked/Inactive. Unguarded: targets dedicated worker PID_UNLINK_WORKER (default av_connectautomation) and SELF-SKIPS if it's not linked on the domain, so CI never reddens. Non-idempotent: re-link via mobile PID_51 on the same domain before each run.
PID_60 | Confirm user sees "Go to Connect Menu" when they have signed up for PersonalID |  | - User should see "Go to Connect Menu" option for the Beta Release but not for Mainline release app | Manual / Deferred | Manual | Deferred | Go to Connect Menu shown for Beta but not Mainline -> needs two APK variants.
PID_61 | Verify user sees device logged out from 1st device when log in 2nd device | 1. Login device 1 2. Login device 2 | - User should recieve push notification indicating that "PID is logged out from device 1" | Manual / Deferred | Manual | Deferred | Device-1 logout push on Device-2 login -> needs two concurrent devices.
PID_62 | Verify user is able to sign up with PID in only device which is greater than or equal to android version 9 |  |  | Manual / Deferred | Manual | Deferred | Sign-up gated to Android >= 9 -> needs a device-version matrix.

## Legend
Status | Meaning
Done | Automated and passing on staging.
To do | In scope; automation not yet written (mobile Maestro phase).
Built - blocked | Test written but cannot run live until a prerequisite exists (e.g. a linked dedicated worker).
Deferred | Not automatable in a single session; tracked as manual (device matrix, 2 devices, timing, build variants).